## Main-Tasks
UNI BONN / 22.02.22
CORDIA Project
Lamine Hafiane
Rough schedule (just an overview!)

Milestones	Main-Tasks	Sub-Tasks	Status	Rough Time expenditure / (one human-resource / WW )	rough estimation of the due-date

Measurement and characterization of the ADCs	DC characteristics (INL/DNL and noise)	Test setup (Hardware / Firmware / Software)	done	14	15.08.22
		Characterization of at least 3 DUTs	ongoing	1
		Characterization of more than 50 DUTs (statistical parameters) / + RE-DESIGN of PCB with socket + IC-packaging	open	6-8
		Radiation and Temperature robustness Test (3 DUTs !! tbd)	open	4
	AC characterization (SNDR and ENOB)	Test setup (Hardware / Firmware / Software) + Sinus generator	open	3
		Characterization of at least 3 DUTs	open	2
	Datasheet and documentations		open	1.5

TEST-ASIC 2 (Analog Backend + ADC)	Design	planning of the Top-level	open	1	15.11.23
		Analog/digital design (including Layout)	open	30
		Top-level Verification	open	1
		signoff (gds submission)	open	1
		Documentations	open	2
	measurement and characterization	Test setup (Hardware / Firmware / Software)	open	10
		measurement	open	8
		Radiation and Temperature robustness Test (3 DUTs !! tbd)	open	4

Allocated human resources	availability factor
Lamine Hafiane	75.00%
Hans Krueger	20.00%
Tomek Hemperek	20.00%
Others/Student !!!	tbd

## time-schedule
		2022		2022					2023		2022
		January	February	March	April	Mai	June	July	August	September	October	November	December	January	February	March	April	Mai	June	July	August	September	October	November	December
Measurement and characterization of the ADCs
TEST-ASIC 2 (Analog Backend + ADC)	Design
	measurement setup
	measurement and characterization

## Sheet2
216
214

9000000	41666.67	42056.07		389.41	0.93%